## Sheet1
COSC1076 ¦ Semester 1 2021 | [5 empty] | Jainam Doshi | Adhiraj Jain | Muhib Hasan | Ryan Samarakoon
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | JAM
Group Member: | Jainam Doshi |  | Progress Classes: | Ahead
Group Member: | Adhiraj Jain |  |  | On-track
Group Member: | Muhib Hasan |  |  | Behind
Group Member: | Ryan Samarakoon |  |  | Way Behind
Tutor:
Class:
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Jainam Doshi | Adhiraj Jain | Muhib Hasan | Ryan Samarakoon
|  |  | Group Formed | yes | Weekly Contribution | Reading the Assignment specification | Discussion on assignment specs | Discussion on assignments specs.
|  |  | MS Team created | yes | Issues | None | None
|  |  | Git Repo created | yes | Other Notes | Only the start of the assigment, so I don’t have any comprensive notes to share :(
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Jainam Doshi | Adhiraj Jain | Muhib Hasan | Ryan Samarakoon
|  | Jainam | Choice of where to use linked list, vector & array |  | Weekly Contribution | Designing ADTs | Implemented some features | Utilising linked list for the hand and vector.
|  | Jainam | Initial Design of ADTs (classes and potential methods) |  | Issues |  | None
|  | Muhib | Main menu |  | Other Notes |  | Implemented Linked List, Node and Tile. | Implemented Main Menu feature
|  | Ryan | User Prompt (for gameplay), but no/minimal error checking | [5 empty] | Done implementing
|  | Adhiraj | Linked List implementation
|  | Jainam | Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | Ahead
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Jainam Doshi | Adhiraj Jain | Muhib Hasan | D
|  | Adhiraj and Jainam | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) | not working | Weekly Contribution | Save to | Load game from file.
|  | Muhib | Initialisation of data strctures for new game (2.3.10) | haven't seen it working | Issues |  | Testing of loading feature with the actual data not done yet. | Done with creating tileBag, and handing tiles to player. Still left with shuffling the tile bag. Added ability to create players.
|  |  | Write Tests Cases for common uses | no | Other Notes
|  | Ryan | Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic (2.3.5 and 2.3.6) | haven't seen it working
|  | Progress | Way Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | A | B | C | C
|  |  | Fully complete implementation and error free | mostly | Weekly Contribution
|  |  | Full error checking of user prompt | good | Issues
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes
|  |  | Final Tests | should be renamed
|  |  | Group Report Written | no.
|  | Progress | On-track